## demo
Start | End | Project | Task
2015-11-15 | 2015-11-20 | Data collection | Use IssueCrawler to expand lists
2015-11-21 | 2015-11-25 | Data collection | Complete INGO databases
2015-11-16 | 2015-12-15 | Data collection | Find all INGO legislation
2015-12-15 | 2015-12-25 | Data collection | Code INGO restrictions
2015-11-15 | 2015-11-25 | Data collection | Develop general INGO survey
2015-11-25 | 2015-12-31 | Data collection | Administer survey
2015-12-25 | 2015-12-31 | Data analysis | Model stability and restrictions
2016-01-01 | 2016-02-02 | Writing | Chapter on formal restrictions (H1)
2016-01-15 | 2016-02-15 | Writing | Paper or chapter on survey results (H3 and H4)
2016-03-16 | 2016-03-19 | Writing | ISA conference in Atlanta
2016-02-01 | 2016-03-01 | Data collection | Historical INGO restrictions in China
2016-02-01 | 2016-03-01 | Data collection | Historical INGO restrictions in Egypt
2016-05-01 | 2016-06-01 | Data collection | Fieldwork in London and Beijing
2016-03-01 | 2016-04-01 | Data analysis | Analyze restrictions in China and Egypt
2016-04-01 | 2016-06-01 | Data analysis | Analyze INGO activities
2016-04-01 | 2016-06-15 | Writing | Chapter on application of restrictions (H2)
2016-05-01 | 2016-07-01 | Writing | Chapter on INGO ideal points (H3)
2016-05-01 | 2016-07-01 | Writing | Chapter on INGO flexibility (H4)
2016-07-01 | 2016-08-01 | Writing | Theory
2016-08-01 | 2016-09-15 | Writing | Conclusion
2016-08-01 | 2016-09-15 | Writing | Introduction